## Instructions
User Acceptance Testing (UAT) - AI-Powered E-Commerce Platform
Purpose | Check that the base shop (cart, checkout, payments, admin) and the five AI agents work correctly BEFORE final submission. Every test is a small task with a clear expected result.
Live shop | https://testv3.websitedemolynk.com/discountv2/
Agent service | https://ai-agents-service-tdhq.onrender.com
How to use | 1) Work through the 'UAT Checklist' sheet from top to bottom. 2) Do the Steps, compare with the Expected result. 3) Choose a Status. 4) Write what actually happened. 5) Fix any Fail, then run that test again. 6) Watch the 'Summary' sheet for progress.
Cells you fill in | Only the yellow cells on the 'UAT Checklist' sheet: Status (column G, dropdown), Actual result / notes (column H) and Tested on (column I). Everything else is fixed.
Example of a filled row | Status = Pass ¦ Actual result = 'Cart total showed Rs 25,100 after setting DALDA quantity to 8' ¦ Tested on = 2026-10-15
Status meanings | Not run = not tested yet. Pass = result matched. Fail = result did not match (describe it). Blocked = could not test (e.g. missing key or access).
Priority meanings | High = must pass before submission. Medium = should pass. Low = nice to have.
Exit criteria | Ready for submission when every High priority test is Pass. The Summary sheet shows this automatically.
Test safely | Use test customers and test products. Use example email addresses you control. Never share API keys, screenshots showing keys, or real customer data.
Known gap to fix | GET /fraud/flagged, GET /fraud/history and POST /fraud/check do not require a key yet (test SEC-06). Add key protection before the final submission.
Rules being tested
Fraud (Agent 4) | Order is Flagged at 50 risk points or more. COD above Rs 20,000 adds 25. 3 or more orders in 10 minutes from one email adds 30. Source: settings at the top of app/agents/fraud_agent.py.
Refund (Agent 1) | Auto-approve: not yet delivered + COD, or delivered within 24 hours and Rs 5,000 or less. Admin decides: bigger amounts, 24 hours to 7 days, unclear messages. Auto-reject: more than 7 days. 'Delivered' means the WooCommerce status Completed. Source: app/agents/refund_agent.py.
Search (Agent 2) | Budget words (under, below, above, 3k) are applied per product. Up to 20 smart searches per minute per visitor. Results are kept for 10 minutes. Source: app/agents/discovery_agent.py and the search snippet.
Onboarding (Agent 5) | Description 60 to 250 words, SEO title up to 60 characters, meta description 110 to 160, 3 to 10 tags, up to 3 attempts. Source: app/agents/onboarding_agent.py.
Pricing (Agent 3) | At least 2 stores needed, up to 3 search rounds, within 5% of the median = keep, at most 15% change, rounded to Rs 5. Source: app/agents/pricing_agent.py.

## UAT Checklist
UAT Checklist
Fill the yellow columns (Status, Actual result / notes, Tested on). Example: Pass ¦ Cart total showed Rs 25,100 ¦ 2026-10-15
ID | Area | Test case | Steps | Expected result | Priority | Status | Actual result / notes | Tested on
CART-01 | Cart | Add a simple product to the cart | Open the shop. Click Add to cart on BESAN 500gm. | Cart icon shows 1 item. Cart total is Rs 100. | High | Not run
CART-02 | Cart | Add a pack-size (variable) product | Open DALDA BANASPATI GHEE. Choose the 5 kg Pouch Carton pack and add it to the cart. | Cart shows the chosen pack size and Rs 3,125 per unit. | High | Not run
CART-03 | Cart | Change the quantity | In the cart, set the DALDA quantity to 8. | Line total is Rs 25,000 and the cart total updates (Rs 25,100 with 1 BESAN). | High | Not run
CART-04 | Cart | Remove an item | Click the bin icon next to one item. | The item disappears and totals are recalculated. | Medium | Not run
CART-05 | Cart | Empty cart | Remove every item from the cart. | An empty-cart message appears and the cart icon shows Rs 0. | Medium | Not run
CART-06 | Cart | Cart survives a page refresh | Add an item, then refresh the page and open another page. | The item is still in the cart. | Medium | Not run
CART-07 | Cart | Coupon codes | Create a test coupon in WooCommerce > Marketing > Coupons. Apply it in the cart, then try a wrong code. | The valid coupon reduces the total. The wrong code shows a clear error. | Low | Not run
CART-08 | Cart | Out-of-stock product cannot be bought | Set a product to Out of stock in the admin. Open it in the shop. | Add to cart is disabled or says Out of stock. | Medium | Not run
CART-09 | Cart | Cart is usable on a phone | Open the cart at phone width (browser dev tools or a real phone). | Layout is readable, buttons are tappable, nothing overlaps. | Low | Not run
CHK-01 | Checkout | Guest checkout with Cash on Delivery | Add a product, go to checkout, fill every field, choose Cash on delivery, click Place Order. | Thank-you page shows the order number, total and payment method Cash on delivery. | High | Not run
CHK-02 | Checkout | Required fields are checked | On checkout, leave the email empty and click Place Order. | A clear error is shown and no order is created. | High | Not run
CHK-03 | Checkout | Order summary matches the cart | Compare the checkout Order summary with the cart. | Items, quantities and total are identical. | High | Not run
CHK-04 | Checkout | Order appears in the admin | Open WooCommerce > Orders after placing an order. | The order is listed with the right customer, items, total and status Processing. | High | Not run
CHK-05 | Checkout | Customer note is saved | Type a note in Add a note to your order and place the order. | The note appears on the order (Customer provided note). | Low | Not run
CHK-06 | Checkout | Order emails are sent | Place an order, then check the order notes and the inbox. | Order notes show 'New order' and 'Processing order' emails sent, and the emails arrive. | Medium | Not run
CHK-07 | Checkout | Logged-in customer checkout | Log in as a customer, place an order, open My Account > Orders. | The order is linked to the account and listed there. | Medium | Not run
CHK-08 | Checkout | No duplicate order on double click | Click Place Order twice quickly. | Only one order is created. | Medium | Not run
CHK-09 | Checkout | Currency displays correctly | Check prices in the shop, cart and checkout (PKR / Rs). | Prices use Rs everywhere and totals are consistent. Switching currency (if enabled) does not break the total. | Low | Not run
PAY-01 | Payments | Only the required payment methods are shown | Open checkout and look at Payment options. | Only Cash on delivery and Direct bank transfer are offered. No card, Stripe or PayPal. | High | Not run
PAY-02 | Payments | Cash on Delivery flow | Place an order with Cash on delivery. | Order is created as Processing and shows 'Pay with cash upon delivery'. | High | Not run
PAY-03 | Payments | Bank transfer flow | Place an order with Direct bank transfer. | Thank-you page shows the bank account details. Order status is On hold. | High | Not run
PAY-04 | Payments | Bank details are correct | Compare the account name and number on the thank-you page and in the order email with your real account. | Details are exactly correct. | High | Not run
PAY-05 | Payments | Mark a bank-transfer order as paid | After payment arrives, change the order from On hold to Processing and update. | Status and order note are saved. | Medium | Not run
PAY-06 | Payments | Online gateways are removed | Open WooCommerce > Settings > Payments. | Stripe, PayPal and other card gateways are disabled or removed. | Medium | Not run
ADM-01 | Admin | Add a product | Products > Add New. Fill name, price, image, category. Publish. | The product appears in the shop with the right price and image. | High | Not run
ADM-02 | Admin | Edit a product price | Change the price of a product and update. | The shop and cart show the new price. | High | Not run
ADM-03 | Admin | Change an order status | Open an order, change Processing to Completed, update. | Status saves, an order note is added and the customer email is sent. | High | Not run
ADM-04 | Admin | Manage customers and users | Open WooCommerce > Customers and Users. | Customers are listed. A user's details or role can be edited. | Medium | Not run
ADM-05 | Admin | Role access | Log in as a Shop manager (not admin). Open the AI Agents pages. | Product-related AI pages work. Plugin and theme settings are not available. | Medium | Not run
ADM-06 | Admin | AI Agents dashboard loads | Open WooCommerce > AI Agents. | Three tables appear (waiting refunds, recent requests, flagged orders) with no error message. | High | Not run
ADM-07 | Admin | Trash a product | Move a product to the trash. | It disappears from the shop and from search results. | Medium | Not run
ADM-08 | Admin | Order search and filters | Search orders by number and by email in WooCommerce > Orders. | The right orders are found. | Low | Not run
ADM-09 | Admin | Admin pages need a login | Log out. Open the WooCommerce > AI Agents address directly. | You are sent to the login page. | High | Not run
FRD-01 | Agent 4 Fraud | Normal order is Safe | Place a Cash on Delivery order of about Rs 3,000 with a normal customer. | Order note: 'Fraud agent: Safe (score 0)'. | High | Not run
FRD-02 | Agent 4 Fraud | High-value COD adds risk points | Place a COD order above Rs 20,000. | Order note shows Safe with score 25 and the reason 'High-value Cash on Delivery order'. | High | Not run
FRD-03 | Agent 4 Fraud | Repeated orders are flagged | Place 4 COD orders above Rs 20,000 within 10 minutes using the same email. | The 4th order is Flagged (score 55 or more), put On hold, with reasons in the order note. | High | Not run
FRD-04 | Agent 4 Fraud | Flagged orders show in the dashboard | Open WooCommerce > AI Agents after the flagged order. | The order is listed under Orders flagged by the fraud agent with score and reasons. | High | Not run
FRD-05 | Agent 4 Fraud | A sleeping agent never blocks an order | Leave the service idle 20+ minutes, then place an order. | The order is still placed (it may take longer). The note shows a result or 'unreachable'. | High | Not run
FRD-06 | Agent 4 Fraud | Each order is checked once | Change an order status twice (e.g. Processing, On hold, Processing). | Only one fraud note exists for the order. | Medium | Not run
FRD-07 | Agent 4 Fraud | Direct API check | Open https://ai-agents-service-tdhq.onrender.com/docs. Run POST /fraud/check with IP 10.0.0.5, COD, amount 45000, checkout_seconds 8. | Result is Flagged with score 95 and four reasons. | Low | Not run
REF-01 | Agent 1 Refund | Refund form loads | Open the Request a Refund page. | Form with order number, email and message is shown. | High | Not run
REF-02 | Agent 1 Refund | Small recent refund is auto-approved | Mark a COD order of Rs 5,000 or less as Completed. Within 24 hours submit the form with a message like 'item damaged, I want a refund'. | Message says Approved with the reason. Dashboard shows status auto_approved. | High | Not run
REF-03 | Agent 1 Refund | Large refund waits for an admin | Complete an order above Rs 5,000. Within 24 hours submit a refund request. | Customer sees 'Received...'. The request appears under Refund and cancel requests waiting for you. | High | Not run
REF-04 | Agent 1 Refund | Admin approves a request | In WooCommerce > AI Agents click Approve on a waiting request. | Notice says status approved. It moves to Recent refund requests. | High | Not run
REF-05 | Agent 1 Refund | Admin rejects with a note | Click Reject on another waiting request with a note. | Status becomes rejected and the note is saved. | High | Not run
REF-06 | Agent 1 Refund | Cancel before delivery (COD) | Place a COD order but leave it Processing. Submit the form with 'please cancel my order'. | Request is approved automatically as a cancellation. | High | Not run
REF-07 | Agent 1 Refund | Refund after 24 hours goes to an admin | Using https://ai-agents-service-tdhq.onrender.com/docs, POST /refund/request with an order that was delivered 3 days ago. | Status is pending_approval with the reason 'outside the 24h auto window'. | Medium | Not run
REF-08 | Agent 1 Refund | Refund after 7 days is rejected | Using /docs, POST /refund/request with delivered_at 10 days ago. | Status is auto_rejected with the 7-day reason. | Medium | Not run
REF-09 | Agent 1 Refund | Wrong email is refused | Submit the form with the right order number but a different email. | Message: could not find an order matching those details. | High | Not run
REF-10 | Agent 1 Refund | Only one request per order | Submit a second refund request for an order that already has one. | Message says a request for this order already exists. | Medium | Not run
REF-11 | Agent 1 Refund | Unclear message goes to an admin | Submit a request with the message 'what is your phone number'. | Request is pending_approval for a person to read. | Medium | Not run
REF-12 | Agent 1 Refund | Approval still works after the service slept | Create a waiting request, leave the service idle 20+ minutes, then click Approve. | Approval succeeds and the status updates. | Medium | Not run
REF-13 | Agent 1 Refund | Customer text cannot run scripts | Submit a refund message containing <script>alert(1)</script>. | The text shows as plain text in the dashboard. No popup appears. | High | Not run
SRCH-01 | Agent 2 Search | Product sync | Open WooCommerce > Sync to AI agents and click Sync all products now. | Message shows the number synced and 0 errors. The count matches your published products. | High | Not run
SRCH-02 | Agent 2 Search | New product is searchable automatically | Publish a new product with a unique name. Wait one minute. Search for it. | It appears in the search results without pressing the sync button. | High | Not run
SRCH-03 | Agent 2 Search | Price change is picked up | Change a product price across a budget limit, then search with that budget. | Results follow the new price. | Medium | Not run
SRCH-04 | Agent 2 Search | Trashed product disappears from search | Trash a product, then search for it. | It is not in the results. | Medium | Not run
SRCH-05 | Agent 2 Search | Budget on the results page | Open https://testv3.websitedemolynk.com/discountv2/?s=cooking+oil+under+3000&post_type=product | Only cooking-oil products priced Rs 3,000 or less are shown, best match first. | High | Not run
SRCH-06 | Agent 2 Search | Two items in one search | Search cooking oil and ghee under 4000 on the site. | Both oil and ghee products are shown, none above Rs 4,000. | High | Not run
SRCH-07 | Agent 2 Search | The search bar dropdown uses the agent | Clear WooCommerce > AI Search Log, type a query in the search bar, reload the log. | Log shows 'agent ranking applied' for the typed text. | High | Not run
SRCH-08 | Agent 2 Search | Roman Urdu / mixed language | Search 'ghee aur oil under 4000'. | Understood as two items with a Rs 4,000 budget. | Low | Not run
SRCH-09 | Agent 2 Search | No match is handled | Search for zzzzqqq. | A normal 'no products found' message, no error. | Medium | Not run
SRCH-10 | Agent 2 Search | Search still works when the agent is asleep | After 20+ minutes idle, search once. | Results appear (normal WordPress search at worst). No blank page or error. | Medium | Not run
SRCH-11 | Agent 2 Search | Out-of-stock products are hidden | Set a product Out of stock, wait a minute, search for it. | It is not suggested by the AI search. | Medium | Not run
SRCH-12 | Agent 2 Search | Search limit is graceful | Run more than 20 different searches within a minute. | Search keeps working (falls back to normal search). No error. | Low | Not run
ONB-01 | Agent 5 Onboarding | Onboarding page loads | Open WooCommerce > AI Product Onboarding. | Form with product name and photo upload is shown. | High | Not run
ONB-02 | Agent 5 Onboarding | Create a draft from a photo | Enter a product name, upload a clear photo, click Create draft with AI. | Green notice with a link. A Draft product exists with title, descriptions, category, tags and the photo. | High | Not run
ONB-03 | Agent 5 Onboarding | The agent really read the photo | Open 'What the agent did' in the notice. | A line starts with 'Gemini Vision saw'. If it says no key or failed, the template was used. | High | Not run
ONB-04 | Agent 5 Onboarding | Description follows the rules | Read the generated description. | 60 to 250 words, mentions the product, no price, no unsupported claims (organic, halal, certified). | High | Not run
ONB-05 | Agent 5 Onboarding | SEO fields are filled | Open the draft and look at the SEO box. | SEO title is 60 characters or less, meta description 110 to 160, focus keyword is set. | Medium | Not run
ONB-06 | Agent 5 Onboarding | Category and tags | Check the draft's category and tags. | Category is one of your existing categories. Tags are sensible and lowercase. | Medium | Not run
ONB-07 | Agent 5 Onboarding | Draft is not public | Open the shop and search for the new product. | It is not visible until a person publishes it. | High | Not run
ONB-08 | Agent 5 Onboarding | Wrong file type is refused | Upload a PDF or GIF. | Friendly message asking for JPG, PNG or WebP. No product is created. | Medium | Not run
ONB-09 | Agent 5 Onboarding | Large photos | Upload a 6 to 10 MB phone photo. Then try a file over 10 MB. | The 6 to 10 MB photo works. The larger file is refused with a message. | Low | Not run
ONB-10 | Agent 5 Onboarding | Claims allowed only when shown | Create a product named 'Organic Honey 500g Jar'. | 'Organic' may appear because it is in the name. For other names it must not appear. | Low | Not run
ONB-11 | Agent 5 Onboarding | Price and stock are left empty | Open the new draft. | Price and stock are empty and the notice reminds you to set them. | Low | Not run
PRC-01 | Agent 3 Pricing | Audit page loads | Open WooCommerce > AI Price Audit. | Dropdown lists products and pack sizes. Recent audits table is shown. | High | Not run
PRC-02 | Agent 3 Pricing | Run an audit | Choose KISAN COOKING OIL 5 Liter and click Audit this product (allow up to a minute). | A new row appears with a suggestion, confidence and the competitor prices. | High | Not run
PRC-03 | Agent 3 Pricing | Prices match the sources | Open two competitor links from the row. | The prices on those pages match what the agent reported (allow small changes over time). | High | Not run
PRC-04 | Agent 3 Pricing | Wrong pack sizes are ignored | Check the competitor list for a 5 liter audit. | No 1 liter or other pack prices are used. | Medium | Not run
PRC-05 | Agent 3 Pricing | Suggestion rules | Compare your price with the median in the row. | More than 5% above the median gives lower, more than 5% below gives raise, otherwise keep. Change is 15% at most and rounded to Rs 5. | Medium | Not run
PRC-06 | Agent 3 Pricing | Minimum price is respected | Audit again with Lowest price I accept above the suggestion. | Suggested price is never below that minimum. | Medium | Not run
PRC-07 | Agent 3 Pricing | Apply this price | Click Apply this price on a lower or raise suggestion and confirm. | Product price changes in WooCommerce and the status becomes applied. | High | Not run
PRC-08 | Agent 3 Pricing | Sale price is protected | Try Apply on a product that has a sale price. | A message asks you to change the price by hand. Nothing changes. | Medium | Not run
PRC-09 | Agent 3 Pricing | Dismiss | Click Dismiss on a suggestion. | Status becomes dismissed and no price changes. | Low | Not run
PRC-10 | Agent 3 Pricing | Duplicate audit reuses the result | Audit the same product again within 10 minutes. | Steps start with 'Reused the audit' and no new search is made. | Low | Not run
PRC-11 | Agent 3 Pricing | No search key or search down | Audit when Tavily is unavailable (or with an invalid key on a test copy). | Result says no_data with a clear reason. No crash. | Medium | Not run
PRC-12 | Agent 3 Pricing | Own website is not a competitor | Read the competitor list. | Your own shop is never listed. | Low | Not run
SEC-01 | Security | No secrets on GitHub | Open the GitHub repo. Check there is no .env file and search for your key text. | No keys or passwords appear anywhere in the repo. | High | Not run
SEC-02 | Security | Site key is required | In https://ai-agents-service-tdhq.onrender.com/docs run POST /recommendations without a site key (only if SITE_API_KEY is set on Render). | Answer is 401 Unauthorized. | High | Not run
SEC-03 | Security | Admin endpoints are protected | In /docs run GET /refund/requests without an admin key. | Answer is 401 Unauthorized. | High | Not run
SEC-04 | Security | Keys live in one place | Check WordPress snippets and Render settings. | Keys are only in the config snippet and Render environment. No other snippet has a key typed in. | High | Not run
SEC-05 | Security | Customers cannot open admin pages | Log in as a normal customer. Open /wp-admin/admin.php?page=ds-agents-dashboard. | Access is denied. | High | Not run
SEC-06 | Security | Fraud endpoints are protected (known gap) | In /docs run GET /fraud/flagged and POST /fraud/check without any key. | EXPECTED: 401. KNOWN GAP: these two endpoints are currently open. Fix before final submission. | High | Not run
SEC-07 | Security | Wake-up after idle | Leave the service idle 20+ minutes. Then open /health. | It answers within about a minute and normal use continues. | Medium | Not run
SEC-08 | Security | Standalone admin page | Open https://ai-agents-service-tdhq.onrender.com/admin. | Either works with the admin key, or returns 404 if DISABLE_ADMIN_PAGE is set. | Low | Not run
DEP-01 | Deployment | Render service is live | Open https://ai-agents-service-tdhq.onrender.com/health. | Shows status ok. | High | Not run
DEP-02 | Deployment | Database is connected | In /docs run GET /catalog/stats with the admin key. | Shows total, in_stock and sample_products 0 after the sync. | High | Not run
DEP-03 | Deployment | Environment variables are set | Check Render > Environment. | DATABASE_URL, GOOGLE_API_KEY, TAVILY_API_KEY, ADMIN_API_KEY and SITE_API_KEY exist with real values (no placeholder). | High | Not run
DEP-04 | Deployment | GitHub repository is complete | Open the repo on GitHub. | Code, README, render.yaml, tests and wordpress/ snippets are there. No .env, no database file. | High | Not run
DEP-05 | Deployment | Automated tests pass | Run the five test files locally (test_fraud, test_refund, test_discovery, test_onboarding, test_pricing). | Every file ends with a passed message. | Medium | Not run
DEP-06 | Deployment | Live website URL works | Open https://testv3.websitedemolynk.com/discountv2/ in a private browser window. | Shop opens normally for visitors (Coming soon mode is off). | High | Not run
DEP-07 | Deployment | Shop stays fast with agents installed | Open the shop, search once and place an order, watching the speed. | No noticeable delay for customers beyond the first request after idle. | Low | Not run

## Summary
UAT Summary (updates automatically)
Area | Total | Pass | Fail | Blocked | Not run | % Passed
Cart | 9 | 0 | 0 | 0 | 9 | 0%
Checkout | 9 | 0 | 0 | 0 | 9 | 0%
Payments | 6 | 0 | 0 | 0 | 6 | 0%
Admin | 9 | 0 | 0 | 0 | 9 | 0%
Agent 4 Fraud | 7 | 0 | 0 | 0 | 7 | 0%
Agent 1 Refund | 13 | 0 | 0 | 0 | 13 | 0%
Agent 2 Search | 12 | 0 | 0 | 0 | 12 | 0%
Agent 5 Onboarding | 11 | 0 | 0 | 0 | 11 | 0%
Agent 3 Pricing | 12 | 0 | 0 | 0 | 12 | 0%
Security | 8 | 0 | 0 | 0 | 8 | 0%
Deployment | 7 | 0 | 0 | 0 | 7 | 0%
TOTAL | 103 | 0 | 0 | 0 | 103 | 0%
High priority tests not yet Pass | 54
Submission status | NOT READY: 54 High priority test(s) not passed

## Test Data
Test data to reuse
Item | Value | Used in
Product: BESAN 500gm | Rs 100 (from your earlier test order) | CART, CHK
Product: DALDA BANASPATI GHEE, 5 kg Pouch Carton | Rs 3,125 each (8 units = Rs 25,000) | CART, FRD, REF
Product: KISAN COOKING OIL, 5 Liter Pouch Carton | Rs 2,875 each (25 units = Rs 71,875) | SRCH, PRC, FRD
Test customer email | Use an email address you control (example: yourname+test1@gmail.com) | CHK, FRD, REF
Search: budget | cooking oil under 3000 | SRCH
Search: two items | cooking oil and ghee under 4000 | SRCH
Search: mixed language | ghee aur oil under 4000 | SRCH
Search: no match | zzzzqqq | SRCH
Refund message: damaged | The ghee carton arrived damaged, I want my money back | REF
Refund message: cancel | Please cancel my order | REF
Refund message: unclear | what is your phone number | REF
Script test text | <script>alert(1)</script> | REF, SEC
Results page address | https://testv3.websitedemolynk.com/discountv2/?s=cooking+oil+under+3000&post_type=product | SRCH
Search debug address | Add &ds_ai_debug=1 to a results page address (admin only) | SRCH
Agent service health | https://ai-agents-service-tdhq.onrender.com/health | DEP, SEC
Agent service test page | https://ai-agents-service-tdhq.onrender.com/docs | FRD, REF, SEC, DEP
Product names and prices come from your earlier test orders; replace them if your catalog changes.